## Tech Adoption
Leverage Lessons Learned Through Failure And Growth
| OLD (variable results) | NEW (consistent results)
Culture / Environment Technology Adoption Lifecycle
| Dominant Culture - Pragmatists/Conservatives - Early/Late Majority | SHIFT EARLIER: - Tech Enthusiasts/Visionaries - Innovator/Early Adopters
| Reacting - Limited annual plan - No investment / testing budget - Ad hoc investment | Planning - Annual Technology Agenda - Directional budget - Focus on desired outcomes
| Reactive or "PUSH" technology process | Proactive and "PULL" technology process
| Distributed accountability and reactive priorities | Single accountability for Now, Near. Far Technology Agenda and PRIORITIES
Plan (Pre-Launch)
| Technology focus set by company leadership | Technology Agenda set by DESIRED OUTCOME of users - Solve an urgent or critical need - Make their job easier - Integrate with current workflow - Enhance communication - Improve productivity
| Senior leaders do not anticipate or plan for failures to quickly adopt or fully-utilize | Pilot / Test - Gated process to orient and align expectations - Determine implement levels for success - Lev 1, Lev , Lev3 - Meet the team where they are for NEED and READINESS - Customer support is a big plus
Do (Launch)
| Limited appreciation for “time scarcity” plus stress level and workload at project | Show Stoppers - How much stress on project team? Do they have the right staff? - “Mental bandwidth” – a team/project might not work for pilot or early launch
| Technology company Training Manual is sufficient | Establish User Group / Training - Meet twice monthly - Collaborate / partner with Tech provider - Living User manual - Continuous improvement - Lean the process
Check (Utilizing) and Adjust/Act
| After launch - accountability shifts to the Project Team | Technology Leader Follow-Up - Champion from project team - Sholuder to shoulder dedicated support - Regular check-ins on progress and share success stories - Is Technology achieving expectations?
| Momentum of early success may fade | Reinforce the Vision - Share success stories - Social media - Quarterly break-out sessions to "spread the word" - Nuture and utilize early adopters as missionaries - Operational leaders are best salesmen - Become leading Tech SME for customers